## Cover Page
School Listing System
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Sai Sreya Palle Neelima Devadi Avuti Nithish Kumar Sandesh Bhoir
| Role | POD Leader, POD Member, POD Member, POD Member
| Signature | Sreya-2065831 Neelima-2066175 Nithish-2065839 Sandesh-2065992
| Date | 2022-02-04
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog - Instructions C3: Protected Controlled Copy
Sprint Backlog
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
Sample
The sheet sample is an example sheet on how to fill the sprint backlog. Trainees can refer it to fill the details in the sheets Sprint 1/2/3.
Sprint 1/2/3
| User Story & Task Id | List the User Story id taken from product backlog that are selected to be completed in the particular sprint & List the number of tasks the User story is split into..
| Task | Name the tasks the user story is split into.
| Story Points | Enter the story points that was given for the user story during Sprint planning
| Assigned to | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5 | Task done in Day1/2/3/4/5 - Sprint review and retrospective to be held on Day 5
| Total | Summation of the estimation per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sample
Sprint Backlog <Contract_Management> Project ID: <INTBGL20ES001/A003> C3: Protected Controlled Copy
USER STORY & TASK ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | User Registration | 8
Task_1 | Create table to store Admin details |  | Ujjal |  | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Design the registration page |  | Vikalp |  | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Design Login page |  | Vaibhav |  | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Develop authentication process for login |  | Vishwas |  | 0.5 | 1 | 2 | 3 | 1 | 0
US_2 | Admin Home | 1
Task_1 | Create table to store Admin details |  | Trainee_3 |  | 3 | 3 | 0.5 | 0.5 | 0 | 0
Task_2 | Design the Admin registration page |  | Trainee_4 |  | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Develop code for authentication |  | Trainee_3 |  | 2 | 2 | 5 | 0 | 1 | 0
Task_4 | Develop code to store the admin details |  | Trainee_4 |  | 5 | 5 | 9 | 5 | 1 | 0
US_3 | Listing courses | 5
Task_1 | Develop code for Admin or vendor to add a course |  | Trainee_1 |  | 8 | 6 | 0 | 0 | 0 | 0
Task_2 | Develop Code ofr Admin or vendor to edit a course |  | Trainee_2 |  | 3 | 1 | 3 | 3 | 3 | 0
Task_3 | Develop code for - On clicking on edit a form should be pop up With valid input clicking on Add/update will update the database |  | Trainee_3 |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1
Task_4 | Develop code for Admin or vendor to activate or deactivate a course |  | Trainee_4 |  | 2 | 0.5 | 0 | 0 | 0 | 0
US_4 |  | 8
Task_1 |  |  |  |  | 9 | 4 | 2 | 2 | 1 | 1
Task_2 |  |  |  |  | 6 | 6 | 3 | 3 | 3 | 1
Task_3 |  |  |  |  | 6 | 2 | 8 | 8 | 1 | 0
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
US_5 |  | 3
Task_1 |  |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1
Task_2 |  |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9
Task_3 |  |  |  |  | 9 | 9 | 9 | 4 | 3 | 3
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0
TOTAL |  |  |  |  | 78 | 60 | 59 | 41 | 20 | 18

## Sprint -1
Sprint Backlog School Listing System C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1 | Home Page | 3
Task_1 | Create home page for admin and user. |  | Sandesh Bhoir |  | 13 | 3 | 2 | 3 | 2 | 3
Task_2 | Create suggestions and login buttons |  | Neelima Devadi |  | 13 | 3 | 3 | 2 | 3 | 2
User Story #2 | Login | 3
Task_1 | Create login page |  | Sai Sreya palle |  | 13 | 3 | 3 | 2 | 2 | 3
Task_2 | Validating the login details of admin |  | Nithish kumar |  | 13 | 2 | 3 | 3 | 3 | 2
Task_3 | Store admin details in database |  | Sandesh Bhoir |  | 13 | 3 | 2 | 2 | 3 | 3
User Story #3 | Admin’s Dashboard | 5
Task_1 | Design view for all schools list |  | Neelima Devadi |  | 14 | 3 | 3 | 3 | 2 | 3
Task_2 | Design view for adding schools |  | Sai Sreya palle |  | 13 | 3 | 2 | 2 | 3 | 3
Task_3 | Design view for review of suggestions |  | Nithish kumar |  | 13 | 3 | 3 | 2 | 3 | 2
User Story #4 | User Suggestion List | 5
Task_1 | Create main suggestion page |  | Sandesh Bhoir |  | 14 | 3 | 2 | 3 | 3 | 3
Task_2 | Design suggestion page for each school |  | Sai Sreya palle |  | 14 | 2 | 4 | 3 | 3 | 2
Task_3 | Styling the suggestion page |  | Neelima Devadi |  | 13 | 2 | 2 | 2 | 4 | 3
User Story #5 | School Database | 5
Task_1 | Create main school listing page |  | Neelima Devadi |  | 13 | 2 | 3 | 3 | 3 | 2
Task_2 | Design description page for each school |  | Sandesh Bhoir |  | 14 | 2 | 3 | 2 | 3 | 4
Task_3 | Styling the school listing page |  | NIthish kumar |  | 13 | 2 | 3 | 2 | 3 | 3
User Story #6 | Add School | 3
Task_1 | Create add school |  | Nithish kumar |  | 13 | 3 | 2 | 3 | 2 | 3
Task_2 | Add or delete description for particular school |  | Neelima Devadi |  | 13 | 3 | 3 | 4 | 1 | 2
Task_3 | Store details in school database |  | Sai Sreya palle |  | 13 | 3 | 2 | 4 | 2 | 2
TOTAL |  |  |  |  | 225 | 45 | 45 | 45 | 45 | 45

## Sprint -2
Sprint Backlog School Listing System Project ID:A016 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_7 | Home Page | 3
Task_1 | Create the homepage(userpage) |  | Sandesh |  | 12 | 3 | 2 | 2 | 2 | 3
Task_2 | Design the view requirements page |  | Neelima |  | 12 | 2 | 3 | 3 | 2 | 2
US_8 | Suggestions Page | 5
Task_1 | Coding to view Requirements |  | Sreya |  | 13 | 3 | 2 | 3 | 2 | 3
Task_2 | Design the view Requirements |  | Nithish |  | 11 | 2 | 3 | 2 | 2 | 2
Task_3 | Store the details in DB |  | Sandesh |  | 12 | 3 | 3 | 2 | 2 | 2
US_9 | School Search Criteria | 5
Task_1 | Coding to view Requirements |  | Neelima |  | 13 | 2 | 3 | 3 | 3 | 2
Task_2 | Design View Requirements |  | Sreya |  | 12 | 2 | 3 | 2 | 3 | 2
Task_3 | Validation |  | Nithish |  | 11 | 2 | 3 | 2 | 2 | 2
US_10 | School List According to Customer's Preferences | 5
Task_1 | Coding to view Requirements |  | Sandesh |  | 13 | 3 | 3 | 3 | 2 | 2
Task_2 | Design view requirment |  | Neelima |  | 11 | 3 | 2 | 2 | 2 | 2
Task_3 | Validation |  | Sreya |  | 11 | 2 | 2 | 3 | 2 | 2
US_11 | All School List | 5
Task_1 | Code to view requirements |  | Sreya |  | 13 | 3 | 2 | 3 | 2 | 3
Task_2 | Design View Requirements |  | Sandesh |  | 12 | 2 | 2 | 3 | 3 | 2
Task_3 | Store the details in DB |  | Neelima |  | 10 | 2 | 2 | 2 | 2 | 2
US_12 | School Info | 5
Task_1 | Code the view requirement |  | Nithish |  | 13 | 2 | 3 | 2 | 3 | 3
Task_2 | Design the view requirement |  | Sreya |  | 13 | 3 | 2 | 3 | 3 | 2
Task_3 | Store the details in DB |  | Sandesh |  | 11 | 2 | 2 | 3 | 2 | 2
US_13 | Contact Us | 5
Task_1 | Code the view requirement |  | Neelima |  | 12 | 2 | 1 | 1 | 3 | 5
Task_2 | Design the view requirement |  | Nithish |  | 10 | 2 | 2 | 1 | 3 | 2
TOTAL |  |  |  |  | 225 | 45 | 45 | 45 | 45 | 45

## Sprint -3
Sprint Backlog Contract Management Project ID:A003 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_16 | Edit or modify contract | 13 |  | completed
Task_1 | Coding |  | Vaibhav, Ujjal |  | 6 | 6 | 0 | 0 | 0 | 0
Task_2 | Design and Requirements |  | Tapubrata, Vikalp |  | 6 | 6 | 0 | 0 | 0 | 0
US_17 | View contract | 13 |  | completed
Task_1 | Coding |  | Vaibhav, Ujjal |  | 4 | 4 | 0 | 0 | 0 | 0
Task_2 | Design and requirements |  | Tapubrata, Vikalp |  | 4 | 4 | 0 | 0 | 0 | 0
US_18 | Manage Service Delivery | 8 |  | completed
Task_1 | Coding |  | Viswas |  | 8 | 5 | 3 | 0 | 0 | 0
Task_2 | Design and requirements |  | Vikalp, Tapubrata |  | 6 | 4 | 2 | 0 | 0 | 0
US_19 | View Delivery status | 5 |  | completed
Task_1 | Coding |  | Viswas, Tapubrata, Ujjal |  | 9 | 3 | 6 | 0 | 0 | 0
Task_2 | Design and requirements |  | Vikalp |  | 2 | 1 | 1 | 0 | 0 | 0
US_20 | Close contract/ extend contract | 13 |  | completed
Task_1 | coding |  | Vaibhav, Ujjal, Viswas |  | 15 | 6 | 6 | 0 | 3 | 0
Task_2 | Design and requirements |  | Vikalp, Tapubrata |  | 6 | 0 | 4 | 0 | 2 | 0
Task_3 | Validation |  | Ujjal |  | 4 | 0 | 3 | 0 | 1 | 0
US_21 | Contract Admin Report | 8 |  | completed
Task_1 | Coding |  | Vaibhav |  | 12 | 1 | 6 | 0 | 2 | 3
Task_2 | Design and requirements |  | Vikalp |  | 6 | 0 | 1 | 0 | 1 | 4
Task_3 | Validation |  | Ujjal, Viswas |  | 9 | 0 | 2 | 0 | 1 | 6
US_22 | Supplier Report | 8 |  | completed
Task_1 | Coding |  | Vikalp, Viswas |  | 12 | 0 | 0 | 4 | 4 | 4
Task_2 | Design and requirements |  | Tapubrata, Vikalp |  | 12 | 0 | 6 | 4 | 1 | 1
Task_3 | Validation |  | Ujjal, Viswas |  | 8 | 0 | 0 | 6 | 2 | 0
US_23 | Contract admin fedback | 8 |  | completed
Task_1 | coding |  | Ujjal, Tapubrata |  | 10 | 0 | 0 | 4 | 4 | 2
Task_2 | Design and requirements |  | Vikalp, Ujjal |  | 8 | 0 | 0 | 4 | 2 | 2
US_24 | View Feedback | 5 |  | completed
Task_1 | Coding |  | Ujjal |  | 5 | 0 | 0 | 0 | 3 | 2
Task_2 | Design and requirements |  | Vikalp |  | 6 | 0 | 0 | 2 | 2 | 2
US_25 | Other Validation | 13 |  | completed
Task_1 | Coding |  | Tapubrata, Ujjal, Vaibhav |  | 12 | 0 | 0 | 6 | 1 | 5
Task_2 | Design and requirements |  | Vikalp |  | 6 | 0 | 0 | 2 | 2 | 2
Task_3 | Validation |  | Viswas |  | 7 | 0 | 0 | 3 | 2 | 2
US_26 | Supplier/Contract Admin logoff | 5 |  | completed
Task_1 | Coding |  | Vaibhav |  | 11 | 0 | 0 | 3 | 6 | 2
Task_2 | Design and requirements |  | Tapubrata |  | 6 | 0 | 0 | 2 | 1 | 3
TOTAL |  |  |  |  | 200 | 40 | 40 | 40 | 40 | 40

## Data (hidden)
In-Progress
Completed
N/A